## NCR Log
NCR_Number | Issue_Date | Supplier_ID | Supplier_Name | PO_Number | Receipt_ID | SKU(s) | Quantity_Affected | NCR_Type | Severity | Dollar_Value | Status | Issued_By | Letter_Sent_Date | Supplier_Response_Due | Description | Notes
NCR-MER-2026-0245 | 02/10/2026 | SUP-0312 | Heartland Bearings LLC | MER-PO-106200 | REC-20260210-004 | BG-33044-A1 | 15 | DMG | Major | $2,797.50 | Resolved | JK | 02/10/2026 | 02/24/2026 | Tier 2 functional damage on 15 bearings — surface gouges | Supplier corrective action accepted 02/22/2026.
NCR-MER-2026-0248 | 02/25/2026 | SUP-0312 | Heartland Bearings LLC | MER-PO-107050 | REC-20260305-002 | BG-33044-A1 | 22 | DMG | Major | $4,081.00 | Closed | JK | 02/25/2026 | 03/11/2026 | Tier 2 functional damage on 22 bearings — corrosion spots | Supplier corrective action accepted 03/09/2026. Triggered Probation recommendation (combined with NCR-0245). Probation applied 03/01/2026 per Joon-ho.
NCR-MER-2026-0250 | 04/08/2026 | SUP-0415 | Great Plains Fasteners | MER-PO-108200 | REC-20260408-001 | FS-12050-A1 | 50 | QTY | Major | $1,250.00 | Sent - Awaiting Response | SM | 04/08/2026 | 04/22/2026 | Band 2 short ship, -12%, safety-critical fasteners
NCR-MER-2026-0251 | 04/14/2026 | SUP-0147 | Consolidated Forge Works | MER-PO-107294 | REC-20260414-003 | FG-91144-A1 | 200 | DOC | Major | $15,600.00 | Sent - Awaiting Response | SM | 04/14/2026 |  | Missing MTR for safety-critical forging. COC received but MTR required for heat number verification.
NCR-MER-2026-0252 | 04/14/2026 | SUP-0312 | Heartland Bearings LLC | MER-PO-108510 | REC-20260414-005 | BG-33044-A1 | 30 | DMG | Major | $5,565.00 | Open | SM |  |  | Tier 2 damage on 30 of 144 safety-critical bearings — machined surface scratches.
NCR-MER-2026-0253 | 04/14/2026 | SUP-0089 | Meridian Steel Supply | MER-PO-106833 | REC-20260414-007 | AX-04827-B2 | 18 | QTY | Critical | $7,650.00 | Sent - Awaiting Response | SM | 04/14/2026 |  | Band 3 critical short -18.75% on safety-critical axle housing. Line-down risk confirmed by Production Planning.