## NCR Log
NCR_Number | Issue_Date | Supplier_ID | Supplier_Name | PO_Number | Receipt_ID | SKUs | Quantity_Affected | NCR_Type | Severity | Dollar_Value | Status | Issued_By | Supplier_Response_Due | Supplier_Response_Date | Corrective_Action_Summary | Internal_Reviewer | Resolution_Notes | Description
NCR-MER-2026-0231 | 03/15/2026 | SUP-0034 | Hartwell Bearing Technologies | MER-PO-104801 | REC-20260315-002 | BG-33044-A1 | 8 | DMG | Major | 1484 | Closed | K.W. | 04/04/2026 | 03/28/2026 | Carrier damage confirmed; carrier claim filed; supplier issued revised packing instructions | Theo Brandt | Closed 04/05/2026 — carrier liability confirmed. Supplier revised inner packing. | Tier 2 damage on 8 of 96 tapered roller bearings — impact dents on outer race. Carrier damage during transit.
NCR-MER-2026-0235 | 03/22/2026 | SUP-0089 | GreatLakes Transmission Parts | MER-PO-104808 | REC-20260322-001 | TR-67801-D1 | 3 | QTY | Major | 1836 | Closed | K.W. | 04/05/2026 | 04/01/2026 | Supplier acknowledged picking error; issued credit memo; balance shipped on MER-PO-104874 | Joon-ho Park | Closed 04/05/2026 — supplier acknowledged picking error. Credit memo received. Balance 3 units confirmed shipped on MER-PO-104874. | Band 2 short ship: ordered 24, received 21 (−3 units, −12.5%) on TR-67801-D1.
NCR-MER-2026-0239 | 04/05/2026 | SUP-0051 | Cascade Fastener Corp | MER-PO-104839 | REC-20260405-003 | FN-33102-B2 | 200 | QTY | Critical | 240 | Closed | K.W. | 04/25/2026 | 04/12/2026 | Supplier acknowledged count error; issued credit. No corrective action beyond count verification. | Joon-ho Park | Closed 04/15/2026 — credit memo received. Supplier acknowledged picking error. | Band 3 short ship on FN-33102-B2: ordered 1000, received 800 (−200 units, −20.0%). Supplier on Probation. Severity elevated to Critical.
NCR-MER-2026-0241 | 04/13/2026 | SUP-0051 | Cascade Fastener Corp | MER-PO-104847 | REC-20260412-001 | FS-22801-A3 | 17 | QTY | Critical | 82.45 | Open | K.W. | 05/02/2026 |  |  | Joon-ho Park |  | Band 1 short ship on safety-critical FS-22801-A3: ordered 500, received 483 (−17 units, −3.4%). Supplier on Probation. Severity elevated to Critical.
NCR-MER-2026-0247 | 04/14/2026 | SUP-0012 | Lakewood Precision Forgings | MER-PO-104821 | REC-20260414-001 | AX-04827-B2, AX-05512-C1, FG-91144-A1 | 4 | MIX | Critical | 52300 | Open | K.W. | 04/21/2026 |  |  | Theo Brandt |  | Missing COC on safety-critical receipt (AX/FG parts). Band 1 short ship on AX-04827-B2 (−4 units, −8.3%). Full receipt quarantined pending COC receipt. Dollar value reflects full quarantined receipt value (340 units across all 3 lines) per SOP 14.3.4 DOC NCR valuation: AX-04827-B2 44×$425 + AX-05512-C1 96×$187.50 + FG-91144-A1 200×$78.
NCR-MER-2026-0248 | 04/14/2026 | SUP-0034 | Hartwell Bearing Technologies | MER-PO-104835 | REC-20260414-002 | BG-33044-A1 | 11 | DMG | Major | 2040.5 | Open | K.W. | 04/28/2026 |  |  | Theo Brandt |  | Tier 2 damage on 11 of 144 BG-33044-A1 tapered roller bearings — impact dents on outer race. Safety-critical part. Material quarantined pending Quality inspection.
NCR-MER-2026-0249 | 04/14/2026 | SUP-0034 | Hartwell Bearing Technologies | MER-PO-104835 | REC-20260414-002 | SL-10922-B1 | 12 | QTY | Minor | 393 | Open | K.W. | 05/05/2026 |  |  | Joon-ho Park |  | Over ship Band B on SL-10922-B1: ordered 288, received 300 (+12 units, +4.2%). Standard part. Excess 12 units staged pending Procurement disposition. Severity Minor. 15 business days for supplier response.