## ncr_log
NCR_Number | Issue_Date | Supplier_ID | Supplier_Name | PO_Number | Receipt_ID | SKUs | Quantity_Affected | NCR_Type | Severity | Dollar_Value | Status | Letter_Sent_Date | Supplier_Response_Due | Supplier_Response_Received_Date | Issued_By | Closed_By | Closure_Date | Notes
NCR-MER-2026-0031 | 03/05/2026 | SUP-0112 | Dawson Precision Machining | MER-PO-104741 | REC-20260305-001 | DS-20481-A3 | 12 | DMG | Major | $4,008.00 | Closed | 03/06/2026 | 03/19/2026 | 03/14/2026 | CY | TB | 04/02/2026 | Tier 2 functional damage on 12 DS-20481-A3 units. Supplier provided root cause (inadequate transit blocking) and corrective action. Closed by Theo Brandt 04/02/2026.
NCR-MER-2026-0039 | 04/02/2026 | SUP-0078 | Crestline Bearing Co. | MER-PO-104851 | REC-20260402-001 | BG-33044-A1 | 22 | QTY | Major | $4,081.00 | Closed | 04/03/2026 | 04/16/2026 | 04/11/2026 | CY | TB | 04/22/2026 | Band 2 short ship, −7.6%, 22 units. Safety-critical severity floor applied (Major). Supplier confirmed pick error at warehouse; corrective action accepted. Closed by Theo Brandt 04/22/2026.
NCR-MER-2026-0044 | 03/28/2026 | SUP-0112 | Dawson Precision Machining | MER-PO-104801 | REC-20260328-001 | DS-20481-A3 | 24 | DOC | Major | $8,016.00 | Overdue - Escalated | 03/30/2026 | 04/11/2026 |  | CY |  |  | Missing COC on DS-20481-A3 safety-critical shipment. 24 units quarantined. Supplier response due 04/11/2026 — no response received as of 05/19/2026. Escalated to Joon-ho Park and Theo Brandt. Supplier placed on Probation 04/02/2026 partly in response to this open NCR. Quarantine status: material remains in Q-HOLD pending COC receipt.
NCR-MER-2026-0058 | 03/18/2026 | SUP-0401 | Greystone Transmission Parts | MER-PO-104812 | REC-20260318-002 | TR-44901-C2 | 36 | HEAT | Critical | $26,784.00 | Overdue - Escalated | 03/19/2026 | 03/24/2026 |  | CY |  |  | Heat number mismatch on TR-44901-C2 safety-critical receipt. 36 units quarantined. Supplier response due 03/24/2026 — no response received. Escalated to Walter Finch 03/25/2026. Supplier suspended 04/28/2026 per Walter Finch authorization. Material remains in Q-HOLD.
NCR-MER-2026-0071 | 04/14/2026 | SUP-0401 | Greystone Transmission Parts | MER-PO-104812 | REC-20260414-003 | TR-44901-C2 | 48 | SUB | Critical | $35,712.00 | Overdue - Escalated | 04/15/2026 | 04/18/2026 |  | CY |  |  | Unauthorized substitution: PO specified TR-44901-C2, received TR-44901-C3 (unapproved revision). 48 units quarantined. Supplier suspended 04/28/2026 — all communication via Joon-ho Park only. No supplier response received.
NCR-MER-2026-0062 | 05/11/2026 | SUP-0318 | Acevedo Driveshaft Components | MER-PO-104935 | REC-20260511-001 | DS-31740-A1 | 60 | HEAT | Critical | $37,680.00 | Overdue - Escalated | 05/12/2026 | 05/14/2026 |  | CY |  |  | Heat number mismatch: MTR lists H46-0119881 only; physical parts show H46-0119881 and H46-0119902. Full receipt quarantined in Q-HOLD. Response due 05/14/2026 — no response received as of 05/19/2026. Re-inspection calendar event was set for 05/14/2026. Escalated to Theo Brandt and Elizabeth Velasquez per Section 16.2.1. Escalated to Walter Finch 05/19/2026 per Section 14.5.1 — 3 business days overdue, no supplier response. Posted in #escalations-meridian 05/19/2026 06:08 CST.