## receiving_log
Receipt_ID | PO_Number | PO_Line | SKU | Safety_Critical | Supplier_ID | Carrier_Name | Arrival_Timestamp | Disposition_Timestamp | Dock_Door | Qty_Ordered | Qty_Claimed_On_Slip | Qty_Received | Variance_Units | Variance_Pct | Variance_Band | Quantity_Action | Condition_Tier | Condition_Action | Photos_Folder | Documentation_Status | Documentation_Action | Heat_Numbers | COC_Filename | MTR_Filename | Disposition | NCR_Number | Coordinator_Initials | Putaway_Authorized_Timestamp | Handoff_Notes | Status | Notes
REC-20260328-003 | MER-PO-104820 | 003 | AX-05312-C1 | Y | SUP-0041 | Yellow Freight | 03/28/2026 07:42 CST | 03/28/2026 09:05 CST | Dock 2 | 360 | 144 | 144 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H45-2298471 | MER-PO-104820_COC.pdf | MER-PO-104820_MTR.pdf | ACCEPTED CLEAN |  | CY | 03/28/2026 09:12 CST |  | Posted | Partial PO fulfillment: this shipment covers PO line 003 only (144 of 360 ordered). Remaining open: 216 units. Lines 001 and 002 remain open.
REC-20260402-001 | MER-PO-104851 | 001 | BG-33044-A1 | Y | SUP-0078 | XPO Logistics | 04/02/2026 08:15 CST | 04/02/2026 10:48 CST | Dock 1 | 288 | 266 | 266 | -22 | -7.6% | Band 2 | Accepted with NCR | Tier 0 | Accepted | N/A | Verified | Accepted | H45-3301184, H45-3301185 | MER-PO-104851_COC.pdf | MER-PO-104851_MTR.pdf | ACCEPTED WITH NCR | NCR-MER-2026-0039 | CY | 04/02/2026 11:02 CST |  | Posted | Band 2 material short, −7.6%, safety-critical. NCR-MER-2026-0039 issued (Major). Line-down risk check completed — Aditi confirmed 22-unit gap within buffer stock. Quality (Theo Brandt) confirmed partial receipt acceptable for traceability chain per Slack 04/02/2026 10:41 CST.
REC-20260410-002 | MER-PO-104877 | 001 | DS-20481-A3 | Y | SUP-0112 | Estes Express | 04/10/2026 09:03 CST | 04/10/2026 11:47 CST | Dock 3 | 96 | 96 | 96 | 0 | 0.0% | Exact | Accepted | Tier 1 | Accepted with notation | photos\REC-20260410-002_20260410\ | Verified | Accepted | H46-0041922, H46-0041923 | MER-PO-104877_COC.pdf | MER-PO-104877_MTR.pdf | ACCEPTED WITH NOTATION |  | CY | 04/10/2026 11:55 CST |  | Posted | Supplier status: Probation since 04/02/2026, reason: 2 Major NCRs DS components. Reggie Lemoine sample inspection passed — findings posted #quality-alerts 04/10/2026 11:22 CST. Tier 1 cosmetic damage on 3 of 18 pallets (16.7%, under 25% threshold). Parts visually intact per dock crew confirmation 04/10/2026 09:44 CST. Photos: REC-20260410-002_20260410.
REC-20260414-001 | MER-PO-104903 | 001 | FS-10044-A1 | Y | SUP-0155 | Old Dominion Freight | 04/14/2026 07:58 CST | 04/14/2026 09:31 CST | Dock 1 | 2400 | 2400 | 2400 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0088341 | MER-PO-104903_COC.pdf | MER-PO-104903_MTR.pdf | ACCEPTED CLEAN |  | CY | 04/14/2026 09:38 CST |  | Posted | Supplier status: Approved as of 02/20/2026 per supplier_master.xlsx Last_Status_Change column.
REC-20260508-002 | MER-PO-104993 | 001 | BG-18830-A1 | Y | SUP-0203 | Saia LTL Freight | 05/08/2026 08:44 CST | 05/08/2026 10:19 CST | Dock 2 | 480 | 240 | 240 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0112904 | MER-PO-104993_COC.pdf | MER-PO-104993_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/08/2026 10:27 CST |  | Posted | Partial PO fulfillment: this shipment covers PO line 001 only (240 of 480 ordered). Supplier confirmed split shipment — balance of 240 units expected week of 05/19/2026. Remaining open lines: 002.
REC-20260511-001 | MER-PO-104935 | 001 | DS-31740-A1 | Y | SUP-0318 | Yellow Freight | 05/11/2026 09:17 CST | 05/11/2026 11:44 CST | Dock 4 | 60 | 60 | 60 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Quarantine - heat number mismatch | Quarantined - safety-critical hold | H46-0119881, H46-0119902 | MER-PO-104935_COC.pdf | MER-PO-104935_MTR.pdf | QUARANTINE — full receipt | NCR-MER-2026-0062 | CY |  |  | Posted | Supplier status: New (3 of 5 minimum receipts complete; 40 days since First_Receipt_Date). 100% inspection by Reggie Lemoine completed. Heat number mismatch: MTR (MER-PO-104935_MTR.pdf) lists H46-0119881 only; physical parts show H46-0119881 and H46-0119902. H46-0119902 not on MTR. Full quarantine per Section 12.6.3. NCR-MER-2026-0062 Critical issued. Escalated to Theo Brandt and Elizabeth Velasquez per Section 16.2.1. Re-inspection calendar event set for 05/14/2026. Supplier response due 05/14/2026 (3 business days).
REC-20260512-001 | MER-PO-104952 | 001 | PK-00112-A1 | N | SUP-0374 | Local Carrier | 05/12/2026 07:31 CST | 05/12/2026 08:14 CST | Dock 1 | 500 | 500 | 500 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted |  |  |  | ACCEPTED CLEAN |  | CY | 05/12/2026 08:19 CST |  | Posted | Full PO fulfillment: both PO lines 001 (PK-00112-A1, 500 units) and 002 (PK-00215-A1, 120 units) received in this shipment. MER-PO-104952 fully fulfilled.
REC-20260512-001 | MER-PO-104952 | 002 | PK-00215-A1 | N | SUP-0374 | Local Carrier | 05/12/2026 07:31 CST | 05/12/2026 08:14 CST | Dock 1 | 120 | 120 | 120 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted |  |  |  | ACCEPTED CLEAN |  | CY | 05/12/2026 08:19 CST |  | Posted | See REC-20260512-001 line 001 notes for PO fulfillment status.
REC-20260515-004 | MER-PO-104877 | 002 | TR-08824-B2 | Y | SUP-0112 | Estes Express | 05/15/2026 08:52 CST | 05/19/2026 11:22 CST | Dock 3 | 48 | 48 | 48 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted |  | Verified | Accepted | H46-0188801 | MER-PO-104877_COC.pdf | MER-PO-104877_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/19/2026 11:31 CST |  | Posted | Supplier status: Probation since 04/02/2026. Sample inspection by Reggie Lemoine completed 05/19/2026 — PASS. Findings posted #quality-alerts 05/19/2026 10:58 CST. Accepted clean.
REC-20260519-001 | MER-PO-104981 | 001 | BR-72014-A2 | Y | SUP-0456 | Saia LTL Freight | 05/19/2026 06:34 CST | 05/19/2026 07:58 CST | Dock 1 | 96 | 96 | 96 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0201001, H46-0201002 | MER-PO-104981_COC.pdf | MER-PO-104981_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/19/2026 08:05 CST |  | Posted | Supplier status: Approved as of 03/15/2026. Safety-critical brake components.
REC-20260519-001 | MER-PO-104981 | 002 | BR-72088-B1 | Y | SUP-0456 | Saia LTL Freight | 05/19/2026 06:34 CST | 05/19/2026 07:58 CST | Dock 1 | 48 | 48 | 48 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0201003 | MER-PO-104981_COC.pdf | MER-PO-104981_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/19/2026 08:05 CST |  | Posted | Supplier status: Approved as of 03/15/2026.
REC-20260519-001 | MER-PO-104981 | 003 | PK-00441-A1 | N | SUP-0456 | Saia LTL Freight | 05/19/2026 06:34 CST | 05/19/2026 07:58 CST | Dock 1 | 96 | 96 | 96 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted |  | MER-PO-104981_COC.pdf |  | ACCEPTED CLEAN |  | CY | 05/19/2026 08:05 CST |  | Posted | Customer override — treated as safety-critical for this PO per Customer_Override flag. COC covers all three lines. New SKU — Template 18 sent to Maribel Ortiz 05/19/2026 07:44 CST; row created at E-03-03.
REC-20260519-002 | MER-PO-104918 | 001 | FL-55200-A1 | N | SUP-0247 | Chemical Transport LLC | 05/19/2026 08:09 CST | 05/19/2026 10:31 CST | Dock 2 | 20 | 20 | 20 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted |  |  |  | ACCEPTED CLEAN |  | CY | 05/19/2026 10:38 CST |  | Posted | Hazmat receipt — SDS on file KLI-SDS-75W140-2025, manifest verified. DTL delivery to LINE-ASMB-02. Chris Wojciechowski notified. DTL arrival posted #planning-meridian 05/19/2026 10:38 CST. Hazmat extended dock-to-stock per Section 17.1.3.
REC-20260519-002 | MER-PO-104918 | 002 | FL-55201-A1 | N | SUP-0247 | Chemical Transport LLC | 05/19/2026 08:09 CST | 05/19/2026 10:31 CST | Dock 2 | 10 | 10 | 10 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted |  |  |  | ACCEPTED CLEAN |  | CY | 05/19/2026 10:44 CST |  | Posted | Hazmat receipt — SDS on file KLI-SDS-80W90-2025, manifest verified. Putaway to D-01-01.
REC-20260519-003 | MER-PO-104820 | 003 | AX-05312-C1 | Y | SUP-0041 | Yellow Freight | 05/19/2026 09:33 CST | 05/19/2026 11:44 CST | Dock 3 | 360 | 216 | 216 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0198221 | MER-PO-104820_COC.pdf | MER-PO-104820_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/19/2026 11:52 CST |  | Posted | Balance shipment — 216 units complete PO line 003 (144 received 03/28/2026 per REC-20260328-003). Supplier status: Approved. Overdue escalation for lines 001 and 002 posted to Aditi and Joon-ho per Section 9.5.
REC-20260519-004 | MER-PO-104968 | 001 | TR-44901-C2 | Y | SUP-0401 | Freight Masters Inc. | 05/19/2026 10:02 CST | 05/19/2026 10:18 CST | Dock 1 | 72 | 72 | 0 | 0 | 0.0% | Exact | Refused |  |  | N/A | [5 empty] | REFUSED AT DOCK |  | CY |  |  | Posted | Supplier status: Suspended 04/28/2026. Refused at dock per Section 15.2.4. Escalated to Joon-ho Park, Darnell Hooks, Elizabeth Velasquez simultaneously. Posted #escalations-meridian. Supplier communication routed to Joon-ho Park only. BOL annotated REFUSED, photo in refusals\.
REC-20260519-005 | MER-PO-104993 | 001 | BG-18830-A1 | Y | SUP-0203 | Saia LTL Freight | 05/19/2026 11:32 CST | 05/19/2026 13:29 CST | Dock 4 | 480 | 240 | 240 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0205441 | MER-PO-104993_COC.pdf | MER-PO-104993_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/19/2026 13:38 CST |  | Posted | Balance shipment — 240 units complete PO line 001 (240 received 05/08/2026 per REC-20260508-002). Supplier status: Approved.
REC-20260519-005 | MER-PO-104993 | 002 | BG-18831-B1 | Y | SUP-0203 | Saia LTL Freight | 05/19/2026 11:32 CST | 05/19/2026 13:29 CST | Dock 4 | 200 | 200 | 200 | 0 | 0.0% | Exact | Accepted | Tier 0 | Accepted | N/A | Verified | Accepted | H46-0205442 | MER-PO-104993_COC.pdf | MER-PO-104993_MTR.pdf | ACCEPTED CLEAN |  | CY | 05/19/2026 13:47 CST |  | Posted | Supplier status: Approved as of 03/01/2026.