## NCR Log
ncr_log.xlsx — Nonconformance Report Master Log (Meridian Plant)
Owner: Theo Brandt (Quality Manager) ¦ SOP Ref: SOP-LOG-MER-02 §14.2 ¦ Current as of: 2026-04-14 13:45 CST (end of shift)
NCR_Number | Supplier_ID | Supplier_Name | PO_Number | SKU | NCR_Type | Severity | Dollar_Value_USD | Issue_Date | Letter_Sent_Date | Letter_Sent_By | Supplier_Response_Due | Supplier_Response_Received_Date | Status | Closure_Date | Root_Cause | Corrective_Action | Disposition_Action | Inspector | Coordinator_Initials | Notes
NCR-2026-HIST-09 | SUP-0041 | Alloy Direct Supply | MER-PO-HIST-01 | DS-7710 | Quantity | Minor | 263.75 | 2026-02-25 | 2026-02-26 | JV | 2026-03-19 | 2026-03-10 | Closed | 2026-03-19 | Miscounted at supplier warehouse | Supplier implemented double-count SOP | No action — within acceptance after recount | TB | JV | Historical; Q1 audit note: closure date in log 03-05 vs email 03-04 — §13.6 correction pending
NCR-2026-0028 | SUP-0041 | Alloy Direct Supply | MULTIPLE | DS-FAMILY | Condition — Cosmetic Pattern | Minor | 0 | 2026-03-25 | 2026-03-26 | JV | 2026-04-16 |  | Open |  | Inadequate pallet wrapping causing cosmetic rub damage on DS-family parts in transit | Enhanced wrap spec under development; photographic evidence of corrective shipments to follow | Parts released — cosmetic only; no functional impact | TB | JV | 15-BD Minor response window; due 2026-04-16; awaiting supplier corrective action response
NCR-2026-0031 | SUP-0117 | Precision Gear Works | MER-PO-8790 | GR-5495 | Quantity — Short Ship | Major | 1791 | 2026-03-31 | 2026-04-01 | JV | 2026-04-14 |  | Open |  |  |  | 51 of 60 GR-5495 received; 9-unit short qty in Quarantine Bay QTN-04 | TB | JV | 10-BD Major response window expires 2026-04-14. No response received as of start of shift.
NCR-2026-0033 | SUP-0117 | Precision Gear Works | MER-PO-8833 | GR-5501 | Condition — Tier 2 Functional Damage | Major | 14025.6 | 2026-04-09 | 2026-04-10 | JV | 2026-04-23 |  | Open |  | Damage consistent with carrier mishandling; investigation ongoing |  | 60 units in quarantine; carrier claim YF-CLM-88214 filed TODAY 2026-04-14 (5-BD window met) | TB | JV | Carrier claim filed today within 5-BD window; 10-BD Major supplier response due 2026-04-23
NCR-2026-0034 | SUP-0203 | ChemLube Industrial | MER-PO-HIST-AX | LB-9905 | Documentation — Missing Packing Slip + COC | Critical | 0 | 2026-04-10 | 2026-04-10 | JV | 2026-04-15 |  | Open |  | Packing slip and COC not included with LB-9905 standard lubricant additive shipment received 2026-04-10 | Supplier to supply missing documents; COC confirms product conformance | 36 drums LB-9905 quarantined in QTN-05 pending Theo Brandt release authorization | TB | JV | Critical NCR per §12.5 (both packing slip and COC absent). 3-BD response window expires TOMORROW 2026-04-15. @evelasquez and @tbrandt notified. MER-PO-8830 (tomorrow's separate hazmat LB-9910 shipment) may proceed independently if SDS+manifest present.
NCR-2026-0035 | SUP-0041 | Alloy Direct Supply | MER-PO-8812 | DS-7740 | Quantity — Short Ship on Safety-Critical Part | Major | 262.5 | 2026-04-14 |  | JV | 2026-04-29 |  | Open |  |  |  | 141 of 144 DS-7740 received; 3-unit short qty in quarantine | TB | JV | Opened 2026-04-14 within 2-hour window. NCR letter not yet sent as of end of shift.