## Receiving Log
receiving_log.xlsx — Inbound Receiving Log (Meridian Plant)
Owner: Darnell Hooks (Receiving Supervisor) ¦ SOP Ref: SOP-LOG-MER-02 §13.1 ¦ Current as of: 2026-04-14 13:45 CST (end of shift)
Receipt_ID | PO_Number | PO_Line | SKU | Part_Description | Supplier_ID | Carrier_Name | Dock_Door | Arrival_Timestamp | Qty_Ordered | Qty_Received | Qty_Variance_Pct | Condition_Tier | Condition_Notes | Qty_Disposition | Condition_Disposition | Doc_Disposition | Overall_Disposition | Safety_Critical_Flag | Heat_Number | COC_On_File | MTR_On_File | Quarantine_Flag | Quarantine_Reason | NCR_Number | NCR_Severity | Putaway_Auth_Timestamp | Putaway_Location | Coordinator_Initials | Status | Notes
REC-20260225-009 | MER-PO-HIST-01 | 1 | DS-7710 | Drivetrain Shaft 7710 | SUP-0041 | Yellow Freight | Dock 2 | 2026-02-25 07:42 | 120 | 120 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | ACCEPT | ACCEPT | Y | H-2026-0312 | Y | Y | N |  | NCR-2026-HIST-09 | Minor | 2026-02-25 11:30 | DS-7 Rack, Bin 4A | JV | Closed | NCR closed; Q1 audit note: log closure date 03-05 vs email 03-04 — §13.6 correction pending
REC-20260318-004 | MER-PO-HIST-02 | 1 | AX-1100 | Axle Shaft, Front Drive (L) | SUP-0041 | XPO Logistics | Dock 1 | 2026-03-18 06:58 | 48 | 48 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | ACCEPT | ACCEPT | Y | H-2026-0388 | Y | Y | N |  |  |  | 2026-03-18 10:45 | AX Rack, Bin 2B | JV | Closed | Q1 audit sample; COC in packing_slips\2026\03\REC-20260318-004_COC.pdf
REC-20260331-001 | MER-PO-8790 | 1 | GR-5495 | Ring Gear, 6-bolt pattern | SUP-0117 | Yellow Freight | Dock 2 | 2026-03-31 08:45 | 60 | 51 | -15.0% | 0 | Clean | SHORT-SHIP | ACCEPT | ACCEPT | SHORT-SHIP | N |  | N/A | N/A | N | NCR-2026-0035 tracks 3-unit shortage; 51 received units are available | NCR-2026-0031 | Major | 2026-03-31 11:30 | GR Rack, Bin 2C (51 units); 9-unit short qty in Quarantine Bay QTN-04 | JV | Open | NCR-2026-0031 Major issued 2026-03-31; letter sent 2026-04-01. 10-BD supplier response window expires 2026-04-14.
REC-20260401-007 | MER-PO-HIST-03 | 1 | DS-7735 | Drivetrain Shaft 7735 | SUP-0055 | Specialized Transport | Dock 3 | 2026-04-01 08:12 | 96 | 96 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | HOLD-DOCS | QUARANTINE | Y | H-2026-0419 | Y | N | Y | MTR missing on initial receipt; supplier given 5 BD per §12.5; MTR received 2026-04-09 |  |  |  | Quarantine Bay QTN-03 | JV | Open | MTR now on file; re-inspection by Theo Brandt pending — awaiting scheduling
REC-20260404-002 | MER-PO-HIST-04 | 1 | DS-7738 | Drivetrain Shaft 7738 | SUP-0041 | XPO Logistics | Dock 1 | 2026-04-04 07:05 | 60 | 60 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | ACCEPT | ACCEPT | Y | H-2026-0429 | Y | Y | N |  |  |  | 2026-04-04 10:22 | DS-7 Rack, Bin 5C | JV | Closed | 10-BD concealed damage window closes TODAY 2026-04-14 — confirm with production floor by EOD
REC-20260407-003 | MER-PO-HIST-05 | 1 | HW-3305 | Lock Nut M8 Gr8 | SUP-0089 | R&L Carriers | Dock 3 | 2026-04-07 09:30 | 800 | 800 | 0.0% | 0 | Clean — Tier 0 on receipt | ACCEPT | ACCEPT | ACCEPT | ACCEPT | N |  | N/A | N/A | N |  |  |  | 2026-04-07 11:00 | HW Rack, Bin 1D (800 units) | JV | Closed | Received clean on 2026-04-07; putaway authorized 800 units to HW-1 Bin 1D.
REC-20260409-005 | MER-PO-8833 | 1 | GR-5501 | Ring Gear, 7-bolt pattern | SUP-0117 | Yellow Freight | Dock 2 | 2026-04-09 10:15 | 60 | 60 | 0.0% | 2 | Functional damage — cracked mounting face on 8 units | ACCEPT | QUARANTINE | ACCEPT | QUARANTINE | N |  | N/A | N/A | Y | Tier 2 carrier damage on 8 units; all 60 units quarantined pending disposition | NCR-2026-0033 | Major |  | Quarantine Bay QTN-02 | JV | Open | NCR-2026-0033 Major issued 2026-04-09; carrier claim YF-CLM-88214 filed TODAY 2026-04-14 (5-BD window met)
REC-20260409-006 | MER-PO-HIST-06 | 1 | GR-5505 | Ring Gear, 8-bolt pattern | SUP-0117 | Yellow Freight | Dock 2 | 2026-04-09 11:00 | 120 | 120 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | HOLD-DOCS | ACCEPT-DOCS-PENDING | N |  | N/A | N/A | N |  |  |  | 2026-04-09 14:30 | GR Rack, Bin 3A | JV | Open | Packing slip discrepancy noted on receipt; §12.4 5-BD supplier doc window expires 2026-04-16; NCR-2026-0036 will be opened on 2026-04-16 if no supplier response received
REC-20260410-001 | MER-PO-HIST-AX | 1 | LB-9905 | Gear Lubricant Additive (std) | SUP-0203 | Hazmat Express | Dock 4 | 2026-04-10 07:48 | 36 | 36 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | HOLD-DOCS | QUARANTINE | N |  | N | N | Y | Packing slip and COC missing on receipt; material quarantined per §12.4 / §13.3 | NCR-2026-0034 | Critical |  | Quarantine Bay QTN-05 | JV | Open | Missing packing slip + COC triggers Critical NCR per §12.5 (both docs absent). NCR-2026-0034 issued 2026-04-10. 3-BD Critical response window expires 2026-04-15. Material holds until Theo Brandt release authorization.
REC-20260414-001 | MER-PO-8813 | 1 | DS-7741 | Drivetrain Shaft 7741 (25mm) | SUP-0041 | XPO Logistics | Dock 1 | 2026-04-14 07:05 | 144 | 144 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | ACCEPT | ACCEPT | Y | H-2026-0441 | Y | Y | N |  |  |  | 2026-04-14 08:45 | DS-7 Rack, Bin 6A | JV | Closed | COC+MTR verified by Theo Brandt; heat H-2026-0441 confirmed
REC-20260414-002 | MER-PO-8812 | 1 | DS-7740 | Drivetrain Shaft 7740 (22mm) | SUP-0041 | XPO Logistics | Dock 1 | 2026-04-14 07:05 | 144 | 141 | -2.1% | 0 | Clean | SHORT-SHIP | ACCEPT | ACCEPT | SHORT-SHIP | Y | H-2026-0441 | Y | Y | Y | NCR-2026-0035 open for 3-unit short ship; quarantine confirmed by M. Ortiz | NCR-2026-0035 | Major |  | Quarantine Bay QTN-01 | JV | Open | NCR-2026-0035 opened 2026-04-14. NCR letter not yet sent as of end of shift.
REC-20260414-006 | MER-PO-8845 | 1 | GR-5510 | Ring Gear, 9-bolt pattern | SUP-0117 | Yellow Freight | Dock 2 | 2026-04-14 09:07 | 200 | 200 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | ACCEPT | ACCEPT | N |  | N/A | N/A | N |  |  |  | 2026-04-14 12:20 | GR Rack, Bin 4B | JV | Closed | Clean receipt; no NCR
REC-20260414-003 | MER-PO-8820 | 1 | HW-3310 | Hex Bolt M10x40 Gr8.8 | SUP-0089 | R&L Carriers | Dock 3 | 2026-04-14 10:32 | 500 | 501 | +0.2% | 0 | Clean | AUTO-ACCEPT | ACCEPT | ACCEPT | ACCEPT | N |  | N/A | N/A | N |  |  |  | 2026-04-14 11:30 | HW Rack, Bin 1A | JV | Closed | Over Band A (<0.5%) auto-accept; no NCR
REC-20260414-004 | MER-PO-8821 | 1 | HW-3320 | Hex Nut M10 Gr8 | SUP-0089 | R&L Carriers | Dock 3 | 2026-04-14 10:32 | 500 | 500 | 0.0% | 0 | Clean | ACCEPT | ACCEPT | ACCEPT | ACCEPT | N |  | N/A | N/A | N |  |  |  | 2026-04-14 11:30 | HW Rack, Bin 1B | JV | Closed | Exact count; clean receipt
REC-20260414-005 | MER-PO-8822 | 1 | HW-3330 | Lock Washer M10 | SUP-0089 | R&L Carriers | Dock 3 | 2026-04-14 10:32 | 1000 | 997 | -0.3% | 0 | Clean | AUTO-ACCEPT | ACCEPT | ACCEPT | ACCEPT | N |  | N/A | N/A | N |  |  |  | 2026-04-14 11:30 | HW Rack, Bin 1C | JV | Closed | Short Band 0 (≤0.5%) auto-accept; no NCR